# Person 3 Interface and Integration Plan

SteelHacks | September 19 and 20, 2026 | Pittsburgh time

Submit by Sunday 10 a.m.  |  Official deadline Sunday 11 a.m.

You own the app screen and connect everyone's work. Put the strongest coder in this role.

# Saturday schedule

| Time | Your task |
| --- | --- |
| Start to 10:15 a.m. | Set up the shared repository and app. Agree on inputs and outputs. |
| 10:15 a.m. to noon | Build the transcript display, speaker selector, and warning card. |
| Noon to 12:30 p.m. | Connect pasted dialogue to analysis and spoken output. |
| 1 to 3 p.m. | Add microphone controls, conversation reset, and error messages. |
| 3 to 5 p.m. | Fix integration problems and test the complete flow. |
| 6 to 8 p.m. | Polish readability and save a stable version. |
| 8 to 9 p.m. | Freeze features, save the working app, and record a backup demo. |
| 9 to 10 p.m. | Verify that the saved app starts from a fresh launch. |

Lunch 12:30 to 1 p.m.  |  Dinner 5 to 6 p.m.  |  Rest after final checks tonight.

# Sunday schedule

| Time | Your task |
| --- | --- |
| 7:30 to 9 a.m. | Run the final app and check the backup video. |
| 9 to 10 a.m. | Check required repository and demo links. |
| 10 to 11 a.m. | Fix submission-blocking problems only. |

Give Person 4 a working app to test. Connect components every 1 to 2 hours.

Team checkpoints: text to warning to voice by 12:30 p.m.; recorded conversation by 3 p.m.; feature freeze at 8 p.m.