# Person 4 Rules Testing and Presentation Plan

SteelHacks | September 19 and 20, 2026 | Pittsburgh time

Submit by Sunday 10 a.m.  |  Official deadline Sunday 11 a.m.

You own sourced rules, test cases, the pitch, and the final submission. Test throughout the day.

# Saturday schedule

| Time | Your task |
| --- | --- |
| Start to 10:15 a.m. | Check submission requirements. Draft the demo and three sourced rules. |
| 10:15 a.m. to noon | Write about 12 test conversations with expected outcomes. |
| Noon to 12:30 p.m. | Test the connected app and record exact problems. |
| 1 to 3 p.m. | Test complete conversations and check highlighted quotes. |
| 3 to 5 p.m. | Re-run tests and share missed concerns and incorrect alerts. |
| 6 to 8 p.m. | Prepare the pitch and submission text using actual test results. |
| 8 to 9 p.m. | Lead rehearsals and coordinate the backup video. |
| 9 to 10 p.m. | Finish the submission package and upload early if possible. |

Lunch 12:30 to 1 p.m.  |  Dinner 5 to 6 p.m.  |  Rest after final checks tonight.

# Sunday schedule

| Time | Your task |
| --- | --- |
| 7:30 to 9 a.m. | Lead the final rehearsal and check all submission requirements. |
| 9 to 10 a.m. | Submit by 10 a.m. and verify the confirmation. |
| 10 to 11 a.m. | Resolve upload or access problems before the 11 a.m. deadline. |

Give Person 2 the rules and give the team reproducible test failures.

Team checkpoints: text to warning to voice by 12:30 p.m.; recorded conversation by 3 p.m.; feature freeze at 8 p.m.